SOFTWARE EFFORT ESTIMATION

Use Case Points (UCP) Analysis

MediCore Hospital Management System

Version 1.0  ·  August 2026

Companion document to: MediCore HMS SRS v1.0

Prepared by: Kelvin Addae Kwarteng  ·  Student ID 22427564

# Table of Contents

# 1. Purpose and Technique Selection

This document estimates the development effort for the MediCore HMS defined in SRS v1.0, using the Use Case Points (UCP) method (Karner, 1993; refinements per Schneider & Winters, 1998). It records the estimation inputs, calculations, assumptions, constraints, and — critically — the scope decisions the estimate forced, satisfying the project brief’s requirement to show how estimation directly influenced final project scope.

## 1.1 Why Use Case Points

| Technique | Assessment for this project | Verdict |
| --- | --- | --- |
| Use Case Points | Requirements are already expressed as actor-driven use cases derivable from the SRS; UCP sizes functional scope early, before design or code exists, and produces auditable arithmetic from documented inputs. | Selected |
| Function Point Analysis | Applicable, but counting ILFs/EIFs/EIs rigorously requires a settled data model; more effort for similar early-stage accuracy on a use-case-shaped specification. | Rejected (higher counting cost) |
| COCOMO II | Requires a size input (KSLOC or FP) that does not yet exist; converting UCP→SLOC would stack two models’ errors. | Rejected (needs size proxy) |
| Story Points | Relative sizing requires a team with an established velocity baseline; a solo/new team has no historical velocity, so points cannot convert to hours defensibly. | Rejected (no velocity history) |
| Expert Estimation | No access to estimators with HMS delivery history; unstructured judgement is not auditable for assessment. | Used only as sanity check |

## 1.2 Method Overview

- UUCW (Unadjusted Use Case Weight): each use case is classified by transaction count — Simple (≤3 transactions, 5 points), Average (4–7, 10 points), Complex (≥8, 15 points).

- UAW (Unadjusted Actor Weight): each actor is classified — Simple (external system via defined API, 1 point), Average (system via protocol/terminal, 2), Complex (human via GUI, 3).

- UUCP = UUCW + UAW.

- TCF (Technical Complexity Factor) = 0.6 + 0.01 × Σ(technical factor value × weight), over 13 factors T1–T13.

- EF (Environmental Factor) = 1.4 − 0.03 × Σ(environmental factor value × weight), over 8 factors E1–E8.

- UCP = UUCP × TCF × EF; Effort = UCP × productivity rate (person-hours per UCP).

# 2. Actor Classification (UAW)

| Actor | Type | Weight | Count × Weight |
| --- | --- | --- | --- |
| Patient | Human via GUI — Complex | 3 | 3 |
| Doctor | Human via GUI — Complex | 3 | 3 |
| Nurse | Human via GUI — Complex | 3 | 3 |
| Pharmacist | Human via GUI — Complex | 3 | 3 |
| Laboratory Technician | Human via GUI — Complex | 3 | 3 |
| Receptionist / Records | Human via GUI — Complex | 3 | 3 |
| Billing Clerk | Human via GUI — Complex | 3 | 3 |
| Management | Human via GUI — Complex | 3 | 3 |
| System Administrator | Human via GUI — Complex | 3 | 3 |
| Family Grantee | Human via GUI — Complex | 3 | 3 |
| Paystack gateway | External system via defined API — Simple | 1 | 1 |
| Email service | External system via defined API — Simple | 1 | 1 |
| UAW (all phases) |  |  | 32 |

# 3. Use Case Inventory and Classification (UUCW)

Use cases are derived from SRS v1.0 Section 3. Transaction counts include the main success scenario plus principal alternate/exception flows. Phase tags follow SRS Section 7.

| ID | Use Case | Primary Actor(s) | Txns | Class | Pts | Phase |
| --- | --- | --- | --- | --- | --- | --- |
| UC-01 | Authenticate, manage session, reset password | All users | 4–6 | Average | 10 | 1 |
| UC-02 | Self-register as patient | Patient | 2–3 | Simple | 5 | 1 |
| UC-03 | Register walk-in patient | Receptionist | 2–3 | Simple | 5 | 1 |
| UC-04 | Maintain patient profile & next-of-kin | Patient, Records | 2–3 | Simple | 5 | 1 |
| UC-05 | Define doctor schedules & generate slots | Sys Admin | 4–6 | Average | 10 | 1 |
| UC-06 | Book appointment | Patient | 4–6 | Average | 10 | 1 |
| UC-07 | Cancel / reschedule appointment | Patient | 4–5 | Average | 10 | 1 |
| UC-08 | Check in patient & manage live queue | Receptionist | 4–7 | Average | 10 | 1 |
| UC-09 | View live queue dashboard | Reception, Doctor | 2 | Simple | 5 | 1 |
| UC-10 | Conduct consultation (notes, diagnosis, sign-off, addendum) | Doctor | 8+ | Complex | 15 | 1 |
| UC-11 | Record vitals | Nurse | 2–3 | Simple | 5 | 1 |
| UC-12 | Maintain allergy list | Doctor, Nurse | 2–3 | Simple | 5 | 1 |
| UC-13 | Write prescription | Doctor | 4–5 | Average | 10 | 1 |
| UC-14 | Dispense prescription (allergy check, FEFO stock, charge posting) | Pharmacist | 8+ | Complex | 15 | 1 |
| UC-15 | Manage drug catalogue & stock receipts | Pharmacist | 4–6 | Average | 10 | 1 |
| UC-16 | Monitor low-stock & expiry alerts | Pharmacist | 2–3 | Simple | 5 | 1 |
| UC-17 | Order laboratory tests | Doctor | 4–5 | Average | 10 | 1 |
| UC-18 | Process lab order (status flow, structured result entry) | Lab Technician | 8+ | Complex | 15 | 1 |
| UC-19 | Review & release results | Doctor | 4 | Average | 10 | 1 |
| UC-20 | Maintain test catalogue | Sys Admin | 2–3 | Simple | 5 | 1 |
| UC-21 | Maintain consolidated invoice (multi-source charge posting, status lifecycle, bed-day accrual) | System, Billing | 8+ | Complex | 15 | 1 |
| UC-22 | Pay online via Paystack (initialise, callback, server-side verification, receipt) | Patient, Paystack | 8+ | Complex | 15 | 1 |
| UC-23 | Record offline payment | Billing Clerk | 2–3 | Simple | 5 | 1 |
| UC-24 | Void invoice / payment with reason | Management | 3 | Simple | 5 | 1 |
| UC-25 | Admit patient & assign bed | Doctor, Nurse | 4–6 | Average | 10 | 1 |
| UC-26 | Transfer & discharge patient | Doctor, Nurse | 4–6 | Average | 10 | 1 |
| UC-27 | Monitor ward occupancy | Nurse, Management | 2 | Simple | 5 | 1 |
| UC-28 | Maintain facility inventory (wards / rooms / beds) | Sys Admin | 4–5 | Average | 10 | 1 |
| UC-29 | Manage users, roles & departments | Sys Admin | 4–6 | Average | 10 | 1 |
| UC-30 | View management dashboards & reports | Management | 4–6 | Average | 10 | 1 |
| UC-31 | View audit log | Mgmt, Sys Admin | 2–3 | Simple | 5 | 1 |
| UC-32 | Send transactional notifications | System, Email svc | 2–3 | Simple | 5 | 1 |
| UC-33 | Grant / revoke family access | Patient, Admin | 4–6 | Average | 10 | 2 |
| UC-34 | View granted information (family portal) | Family Grantee | 2–3 | Simple | 5 | 2 |

## 3.1 UUCW Summary

| Classification | Weight | Count | Subtotal |
| --- | --- | --- | --- |
| Simple (≤3 txns) | 5 | 14 | 70 |
| Average (4–7 txns) | 10 | 15 | 150 |
| Complex (≥8 txns) | 15 | 5 | 75 |
| UUCW (all phases) |  | 34 | 295 |
| UUCW (Phase 1 = all except UC-33, UC-34) |  | 32 | 280 |

Unadjusted Use Case Points: UUCP(full) = 295 + 32 = 327.  UUCP(Phase 1) = 280 + 29 = 309 (Family Grantee actor excluded).

# 4. Technical Complexity Factor (TCF)

| ID | Factor | Weight | Value (0–5) | W×V | Justification |
| --- | --- | --- | --- | --- | --- |
| T1 | Distributed system | 2 | 3 | 6 | Browser client, REST API, managed DB, two external services — standard 3-tier distribution |
| T2 | Response-time objectives | 1 | 3 | 3 | Interactive targets (NFR-PER-01/-02); no hard real-time |
| T3 | End-user efficiency | 1 | 4 | 4 | Nine role-specific consoles; reception and pharmacy are throughput-critical |
| T4 | Complex internal processing | 1 | 3 | 3 | Slot generation, FEFO stock, bed-day accrual, invoice aggregation — moderate algorithms |
| T5 | Reusable code objective | 1 | 3 | 3 | Slot engine reused for lab visits; shared policy layer (AC-06) |
| T6 | Easy to install | 0.5 | 4 | 2 | Single documented setup path required (NFR-MNT-05) |
| T7 | Easy to use | 0.5 | 4 | 2 | Mixed-skill hospital staff; 3-minute receptionist task target (NFR-USA-03) |
| T8 | Portability | 2 | 2 | 4 | Web-only; single managed DB vendor; modest portability need |
| T9 | Easy to change | 1 | 4 | 4 | Phased roadmap guarantees change; migrations and layering mandated |
| T10 | Concurrency | 1 | 4 | 4 | Contended slot booking and bed assignment must be race-safe (FR-APT-04, FR-FAC-03) |
| T11 | Security objectives | 1 | 5 | 5 | RBAC + ReBAC, permission matrix, audit log, payments, health-data privacy — the system’s defining burden |
| T12 | Direct third-party access | 1 | 3 | 3 | Paystack webhooks and email provider integration |
| T13 | Special user training | 1 | 1 | 1 | Training limited to a user manual and seeded demo walkthrough |
| Σ (W×V) |  |  |  | 44 | TCF = 0.6 + 0.01 × 44 = 1.04 |

# 5. Environmental Factor (EF)

| ID | Factor | Weight | Value (0–5) | W×V | Justification |
| --- | --- | --- | --- | --- | --- |
| E1 | Familiarity with the development process | 1.5 | 3 | 4.5 | Formal SDLC followed for the first time at this rigour; concepts known from coursework |
| E2 | Application (domain) experience | 0.5 | 2 | 1.0 | No prior hospital-systems delivery; domain learned during requirements work |
| E3 | OO / paradigm experience | 1 | 4 | 4.0 | Solid experience with the chosen web stack and ORM patterns |
| E4 | Lead analyst capability | 0.5 | 3 | 1.5 | Requirements analysis performed by the developer; supervisor review available |
| E5 | Motivation | 1 | 5 | 5.0 | Assessed capstone project; high stakes |
| E6 | Stable requirements | 2 | 3 | 6.0 | Scope already underwent one major expansion (clinic → HMS) before baseline; SRS v1.0 now frozen under change control, but volatility is demonstrated |
| E7 | Part-time workers | −1 | 3 | −3.0 | Development is part-time alongside other academic commitments |
| E8 | Difficult programming language | −1 | 1 | −1.0 | Mainstream, well-documented stack |
| Σ (W×V) |  |  |  | 18 | EF = 1.4 − 0.03 × 18 = 0.86 |

## 5.1 Productivity Rate (Schneider–Winters check)

Count environmental factors E1–E6 with value below 3, plus E7–E8 with value above 3: only E2 qualifies (1 factor). With ≤2 such factors, the standard rate of 20 person-hours per UCP applies for a conventional commercial team. This is the baseline rate used in Section 6; Section 7 derives a context-adjusted rate for this project’s actual delivery mode.

# 6. Estimation Results (Commercial Baseline)

UCP = UUCP × TCF × EF = UUCP × 1.04 × 0.86 = UUCP × 0.8944. Effort at the standard 20 PH/UCP; person-months assume 160 productive hours per month.

| Scope | UUCP | UCP | Effort @20 PH/UCP | Person-months |
| --- | --- | --- | --- | --- |
| Full system (Phases 1–2) | 327 | 292 | ≈ 5,850 PH | ≈ 36.6 PM |
| Phase 1 (v1.0, per SRS §7) | 309 | 276 | ≈ 5,520 PH | ≈ 34.5 PM |
| Core increment (defined §8.2) | 190 | 170 | ≈ 3,400 PH | ≈ 21.3 PM |

## 6.1 Sensitivity Analysis

UCP literature reports productivity between 15 and 28 PH/UCP depending on team and risk profile. The estimate is therefore a range, not a point:

| Rate (PH/UCP) | Full system (292 UCP) | Phase 1 (276 UCP) | Core (170 UCP) |
| --- | --- | --- | --- |
| 15 (optimistic) | 4,380 PH | 4,140 PH | 2,550 PH |
| 20 (baseline) | 5,840 PH | 5,520 PH | 3,400 PH |
| 28 (pessimistic) | 8,176 PH | 7,728 PH | 4,760 PH |

## 6.2 Interpretation

At commercial productivity, Phase 1 alone represents roughly 34 person-months — e.g., a 4-person professional team for 8–9 months. This is consistent with market reality for hospital management systems and is the headline finding of this estimation: the full SRS scope is far beyond a single developer’s academic timeline at commercial delivery standards. Every scope decision in Section 9 flows from this result.

# 7. Context-Adjusted Estimate for This Project

The 20 PH/UCP baseline embeds costs this project does not carry: team communication and coordination overhead, organisational ceremony, production-hardening for real clinical deployment, and 1990s-era tooling assumptions. This project is a single developer using a modern batteries-included stack (framework scaffolding, ORM, component libraries), AI-assisted development, managed PaaS hosting (no ops engineering), sandbox integrations, and an academic quality bar (essential-path hardening rather than full production certification).

On that basis a working range of 4–6 PH/UCP is adopted for planning, with the explicit caveat that it is an assumption to be validated, not a measured fact — Section 10 defines the recalibration procedure that replaces this assumption with actuals by mid-project.

| Scope | @4 PH/UCP | @5 PH/UCP | @6 PH/UCP |
| --- | --- | --- | --- |
| Phase 1 (276 UCP) | 1,104 PH | 1,380 PH | 1,656 PH |
| Core increment (170 UCP) | 680 PH | 850 PH | 1,020 PH |

Capacity comparison: at a sustainable 30 hours/week, one academic term (≈15 working weeks) supplies ≈450 person-hours. Even under the most optimistic adjusted rate, Phase 1 (≥1,104 PH) exceeds one term by a factor of ≈2.5, and the Core increment (≥680 PH) exceeds it by ≈1.5. The estimate therefore mandates either a longer delivery window or a smaller assessed increment — this is the decision the estimation forces, documented in Sections 8 and 9.

# 8. Delivery Options and Plan

## 8.1 Options Considered

| Option | Description | Effort fit | Verdict |
| --- | --- | --- | --- |
| A | Two-term solo delivery: Core increment live by end of Term 1 (v0.9); remainder of Phase 1 in Term 2 (v1.0). ≈900 PH capacity vs. 1,104–1,656 PH need — tight but viable at the optimistic end with recalibration checkpoints. | Marginal–feasible | Recommended |
| B | Single-term solo delivery of all of Phase 1. | Infeasible (450 vs. ≥1,104 PH) | Rejected by the numbers |
| C | Team of 3 delivering Phase 1 in one term: ≈1,350 PH combined capacity vs. 1,104–1,656 PH need. | Feasible at optimistic–mid rates | Viable if team formation is permitted |

## 8.2 The Core Increment (v0.9) — Definition

The Core increment is the smallest end-to-end slice that exercises every architectural risk (auth/RBAC, transactional booking, clinical records, stock, multi-source billing, external payment API): UC-01 through UC-10, UC-13, UC-14, UC-15, UC-21, UC-22, UC-23, UC-29, UC-32. It delivers the complete outpatient journey — register → book → queue → consult → prescribe → dispense → invoice → pay (sandbox) — leaving laboratory, admissions/beds, vitals/allergies, dashboards, and audit viewer to complete Phase 1 in Term 2.

Core increment size: UUCW 170 + UAW 20 (Patient, Doctor, Pharmacist, Receptionist, Billing Clerk, System Administrator, Paystack, Email) = UUCP 190 → UCP 170 → 680–1,020 PH at the adjusted rate.

## 8.3 Milestone Plan (Option A)

| Milestone | Contents | Target |
| --- | --- | --- |
| M1 (wk 6, T1) | Auth/RBAC + policy layer, registration, schedules & slots, booking with double-booking guard | First recalibration point |
| M2 (wk 11, T1) | Queue & check-in, consultation, prescriptions, dispensing with FEFO | Second recalibration |
| M3 (wk 15, T1) | Invoicing engine, Paystack sandbox, offline payments, notifications → v0.9 deployed live | Core increment live |
| M4 (wk 6, T2) | Laboratory loop (order → result → release), vitals & allergies | — |
| M5 (wk 11, T2) | Facility/bed management, admissions, transfers, discharge, bed-day billing | — |
| M6 (wk 15, T2) | Dashboards, audit viewer, void workflow, hardening, full test evidence → v1.0 | Phase 1 complete |

# 9. How the Estimation Influenced Project Scope

The project brief requires explicit evidence that estimation shaped scope. The decisions below were taken because of the numbers in Sections 6–7, and each is recorded in the SRS:

| Decision | Estimation driver | Recorded in |
| --- | --- | --- |
| Family-access module deferred to Phase 2 | Removes 16 UCP (UC-33/34 + actor) and the highest consent-model design risk from the assessed build | SRS §7, §3.9 |
| Delivery split into Core increment (v0.9) → Phase 1 (v1.0) | Phase 1 (≥1,104 PH) exceeds one-term capacity (450 PH) ≈2.5×; Core is the largest slice that fits two recalibrated terms | This doc §7–8 |
| SMS deferred; email-only notifications in v1 | Avoids a third external integration; T12 and integration test surface held down | SRS §1.2, §2.5 |
| NHIS/insurance claims → Phase 3 | Claims adjudication would add multiple Complex use cases (≈45+ UCP) and a compliance workstream | SRS §7 |
| Payments run in Paystack sandbox only | Removes production-hardening (settlement, disputes, reconciliation) from the quality bar priced into 20 PH/UCP | SRS §2.5 |
| Radiology shares lab workflow; imaging (PACS) out of scope | Imaging storage/viewer would introduce new Complex UCs and infrastructure cost | SRS §1.2, App. A |
| Lab-visit slot scheduling, break-glass, controlled-drug dual authorisation, duplicate merge, CSV export → Phase 2 | Sub-features inside Phase 1 use cases; deferring trims transactions while classifications (and thus the estimate) stay conservative | SRS §7 |
| Single facility; no multi-branch federation | Multi-tenancy would raise T8/T10 and the data-partitioning design cost | SRS §1.2 |

# 10. Assumptions, Constraints and Estimation Risk

## 10.1 Assumptions

- 160 productive hours per person-month; 30 sustainable hours/week for the developer; ≈15 effective weeks per term.

- Transaction counts reflect the main scenario plus principal alternates as specified in SRS v1.0; Phase 2 sub-feature deferrals were not used to downgrade any use-case classification (estimate is conservative).

- The adjusted 4–6 PH/UCP rate assumes modern framework scaffolding, AI-assisted development, managed hosting, and academic-grade hardening; it is a planning assumption pending calibration (§10.4).

- Requirements remain frozen at SRS v1.0 under change control; any accepted change triggers re-estimation.

## 10.2 Constraints

- Fixed academic calendar; assessment deadlines are immovable.

- Zero-budget hosting; free-tier limits accepted (SRS §2.5).

- Solo development by default (Option A); team formation subject to course rules.

## 10.3 Known Limitations of the Method

- UCP is insensitive to cross-cutting non-functional burden: the permission matrix, ReBAC checks, and audit logging permeate every use case but are captured only through T11 = 5. Residual risk of underestimate; mitigated by the conservative classification policy and milestone recalibration.

- Transaction counting has subjective boundaries; counts and rationale are recorded per use case in Section 3 so the assessor can audit the classification.

- No historical calibration data exists for this developer; the first six weeks of actuals are therefore the most important estimation artefact this project will produce.

## 10.4 Re-estimation and Tracking Plan

- Actual hours are logged per use case from day one (time-tracking tool export archived with project evidence).

- At M1 (week 6): compute personal PH/UCP from completed use cases; if the projected Phase 1 completion misses M3/M6 by more than 20%, invoke the scope-reduction ladder below with supervisor sign-off.

- Scope-reduction ladder (applied in order, smallest cut first): (1) dashboards reduced to two KPIs; (2) audit viewer deferred to Phase 2; (3) transfers deferred (admit/discharge only); (4) lab release step simplified to auto-release with doctor notification.

- Re-estimation is repeated at every milestone; final report compares estimate vs. actuals and states the measured PH/UCP as the project’s calibration contribution.

# 11. Conclusion

The full MediCore scope measures 292 UCP (≈5,850 commercial person-hours; ≈3 person-years) and Phase 1 measures 276 UCP (≈5,520 PH). These numbers made the original ambition — full Phase 1 in a single solo term — demonstrably infeasible and drove the documented restructuring of the project: a two-term plan delivering a live 170-UCP Core increment (v0.9) at the end of Term 1 and the complete Phase 1 system (v1.0) at the end of Term 2, with milestone-based recalibration replacing assumptions with measured productivity. The estimate’s fingerprints on the final scope are itemised in Section 9 and cross-referenced in SRS v1.0 §7.